## 0. SUMMARY & OVERVIEW
CUSTOMER ONBOARDING CHECKLIST - SUMMARY & OVERVIEW
📋 DOCUMENT PURPOSE
This checklist helps customer prepare all required data and information before onboarding to the Tire Performance Monitoring System. ✅ Complete this checklist BEFORE system go-live ✅ Gather all data templates and documents ✅ Coordinate with all stakeholders (Fleet Manager, Supervisors, Operators, IT) ✅ Expected completion time: 1-2 weeks with dedicated effort
📊 CHECKLIST STRUCTURE
Sheet | Topic | Items | Estimated Time | Priority
Sheet 1 | Role & User Access | 5 roles + user list | 2-3 hours | HIGH
Sheet 2 | Vehicle Master Data | 20 data fields per vehicle | 1-2 days | CRITICAL
Sheet 3 | Tire Master Data | 25 data fields per tire | 2-3 days | CRITICAL
Sheet 4 | Supporting Master Data | Locations, Brands, Suppliers, Codes | 4-6 hours | MEDIUM
Sheet 5 | SOP & Training | 22 training/documentation items | Throughout project | HIGH
Sheet 6 | Timeline & Milestones | 3-4 week project plan | N/A - Reference | INFO
Sheet 7 | Pre-Go-Live Checklist | 25 final verification items | Final week | CRITICAL
⚠️ CRITICAL SUCCESS FACTORS
Priority | Item | Why Critical
🔴 P0 | Accurate vehicle & tire serial numbers | Foundation of entire system - errors here cascade everywhere
🔴 P0 | Current KM/HM readings must be accurate | All calculations depend on correct baseline
🔴 P0 | RTD measurements for installed tires | Enables predictive maintenance from day 1
🟠 P1 | Complete user training | System is only as good as data entered
🟠 P1 | Barcode implementation | 10x faster data entry, reduces errors
🟡 P2 | Historical data (optional but valuable) | Better predictions with historical context
💡 HELPFUL TIPS
1. START EARLY: Begin data collection 2-3 weeks before planned go-live 2. ASSIGN DEDICATED PIC: Have 1 person coordinate all data collection 3. VERIFY AS YOU GO: Don't wait until the end to check data quality 4. BARCODE EARLY: Apply barcode stickers to tires as soon as possible 5. INVOLVE OPERATORS: Get buy-in from people who will use the system daily 6. KEEP IT SIMPLE: Focus on required fields first, optional data can come later 7. ASK QUESTIONS: CPH support is available to help clarify any requirements
📞 SUPPORT CONTACT
Project Manager: [Name] Email: support@capio.id Phone/WhatsApp: [Number] Response Time: <24 hours (business days)

## 1. Role & Akses Customer
CHECKLIST ROLE & AKSES — EKSTERNAL (CUSTOMER)
No | Role Customer | Deskripsi | Hak Akses / Menu | Kewajiban | Jumlah User | Status
1 | Fleet Manager / PIC Utama | Penanggung jawab utama fleet management. Memiliki akses penuh untuk monitoring dan decision making. | • Dashboard (full access) • Report & Export (semua data) • Master Data (view & edit) • User Management (assign role) • Examination Report (view/cetak) • Cost Analysis • Predictive Maintenance Alert | • Menunjuk user yang diberi akses • Validasi data master • Review report bulanan • Approve budget tire replacement • Koordinasi dengan CPH | 1-2 orang | ☐ Siap
2 | Supervisor / Koordinator Lapangan | Pengawas lapangan yang bertanggung jawab atas kondisi ban dan kendaraan di area operasi. | • Dashboard (area/region sendiri) • Movement History (view) • Examination (view & input) • Tire Installation/Removal (approve) • Alert Notification (receive) • Master Data (view) | • Supervisi inspeksi harian • Approve tire movement • Report anomali ke Fleet Manager • Koordinasi dengan driver & mekanik • Pastikan SOP diikuti | 2-5 orang | ☐ Siap
3 | Admin / Operator Bengkel | Petugas input data instalasi, removal, dan inspeksi ban di bengkel/workshop. | • Tire Installation Form • Tire Removal Form • Tire Rotation Form • Inspection Form • Master Data (view) • Upload Photos • Barcode Scanner Access | • Input data pemasangan/pelepasan • Input data inspeksi • Scan barcode tire • Upload foto kondisi ban • Pastikan data HM/KM akurat • Report error/anomali | 3-10 orang | ☐ Siap
4 | Driver / Operator Kendaraan | Pengemudi yang melakukan inspeksi harian dan melaporkan kondisi ban. | • Mobile App (simple) • Daily Inspection Form • Quick Report (damage/issue) • View Own Vehicle Status • Receive Maintenance Alert | • Inspeksi ban setiap hari • Report kerusakan segera • Pastikan tekanan angin sesuai • Ikuti instruksi maintenance • Lapor jika ada masalah | 10-50 orang | ☐ Siap
5 | Viewer / Management | Akses read-only untuk monitoring performa fleet tanpa input data. | • Dashboard (view only) • Report (view only) • Export Data (download) • Cost Summary • Performance Metrics | • Tidak ada kewajiban input • Review performa fleet • Provide feedback & improvement ideas | 1-5 orang | ☐ Siap

## 2. Data Master Kendaraan
CHECKLIST DATA MASTER KENDARAAN
No | Field / Kolom Data | Deskripsi | Format / Contoh | Mandatory | Sumber Data | Validasi | Template Excel | Status | Catatan
1 | No. Polisi / License Plate | Nomor polisi kendaraan (unique identifier) | DD 9999 RI, B 1234 ABC | ✓ Wajib | BPKB, STNK | Unique, uppercase, no duplicate | ☐ Tersedia | ☐ Complete
2 | Vehicle Name / Alias | Nama/kode internal kendaraan (optional) | Truck-001, Hauler-A-05 | ○ Optional | Internal system | Alphanumeric | ☐ Tersedia | ☐ Complete
3 | Brand / Merk | Merk kendaraan | Hino, Mitsubishi, Isuzu, Volvo | ✓ Wajib | STNK | From master list | ☐ Tersedia | ☐ Complete
4 | Model / Type | Type/model kendaraan | FM 260 Ti, Fuso FN 517, Giga FVZ 285 | ✓ Wajib | STNK | Alphanumeric | ☐ Tersedia | ☐ Complete
5 | Year / Tahun Pembuatan | Tahun pembuatan kendaraan | 2020, 2021, 2022 | ✓ Wajib | STNK | 4 digit, 1990-2026 | ☐ Tersedia | ☐ Complete
6 | Axle Configuration | Konfigurasi as roda (menentukan jumlah ban) | 6x2, 6x4, 8x4, 10x4, Trailer 3-axle | ✓ Wajib | Spec sheet | From predefined list | ☐ Tersedia | ☐ Complete
7 | Total Tire Positions | Total posisi ban (hitung otomatis dari axle) | 10, 12, 14, 18, 22 | Auto | System | Integer, 6-22 | N/A | N/A | Auto-filled
8 | Curb Weight (kg) | Berat kosong kendaraan | 8500, 12000 | ✓ Wajib | STNK, spec | Numeric, >0 | ☐ Tersedia | ☐ Complete
9 | Max Payload (kg) | Kapasitas angkut maksimal | 15000, 20000, 25000 | ✓ Wajib | STNK, spec | Numeric, >0 | ☐ Tersedia | ☐ Complete
10 | GVW - Gross Vehicle Weight (kg) | Berat total (curb + payload) | 25000, 35000 | Auto | System | Curb + Payload | N/A | N/A | Auto-filled
11 | Engine Number | Nomor mesin | W04D-TL123456 | ○ Optional | STNK | Alphanumeric | ☐ Tersedia | ☐ Complete
12 | Chassis Number / VIN | Nomor rangka | MHFCG3XXXXXXX | ✓ Wajib | STNK | Alphanumeric, unique | ☐ Tersedia | ☐ Complete
13 | Odometer / Current KM | Kilometer saat ini (data awal) | 125000, 58000 | ✓ Wajib | Dashboard kendaraan | Numeric, ≥0 | ☐ Tersedia | ☐ Complete
14 | Hour Meter / Current HM | Hour meter saat ini (jika ada) | 5500, 12000 | ○ Optional | Dashboard (alat berat) | Numeric, ≥0 | ☐ Tersedia | ☐ Complete
15 | Location / Area Operasi | Lokasi/area operasi utama | Jakarta - Warehouse A, Site Kalimantan | ✓ Wajib | Ops manager | From location master | ☐ Tersedia | ☐ Complete
16 | Department / Cost Center | Departemen atau cost center | Fleet-01, Mining-KAL, Logistics-JKT | ○ Optional | Finance/Accounting | Alphanumeric | ☐ Tersedia | ☐ Complete
17 | Usage Type / Segmen | Jenis penggunaan kendaraan | Hauling, Distribution, Mining, Construction | ✓ Wajib | Ops manager | From predefined list | ☐ Tersedia | ☐ Complete
18 | Average Daily KM | Rata-rata KM per hari (estimasi) | 150, 200, 300 | ○ Optional | Historical data | Numeric, 0-1000 | ☐ Tersedia | ☐ Complete
19 | PIC / Responsible Person | Penanggung jawab kendaraan | Ahmad Supervisor, Budi Manager | ○ Optional | HR/Ops | Text | ☐ Tersedia | ☐ Complete
20 | Status Kendaraan | Status operasional saat ini | Active, Standby, Under Repair, Sold | ✓ Wajib | Ops manager | From predefined list | ☐ Tersedia | ☐ Complete

## 3. Data Master Ban
CHECKLIST DATA MASTER BAN (TIRE INVENTORY)
No | Field / Kolom Data | Deskripsi | Format / Contoh | Mandatory | Sumber Data | Validasi | Template Excel | Status | Catatan
1 | Serial Number / Tire ID | Nomor seri ban (unique, 14 digit) | 12345678901200, 98765432109876 | ✓ Wajib | Barcode pada ban | 14 digit, numeric, unique | ☐ Tersedia | ☐ Complete | CRITICAL
2 | Brand / Merk Ban | Merk/brand ban | MRF, Bridgestone, Michelin, Dunlop, GT | ✓ Wajib | Sidewall ban | From brand master | ☐ Tersedia | ☐ Complete
3 | Tire Size | Ukuran ban | 10.00R20, 11.00R20, 295/80R22.5, 12.00R24 | ✓ Wajib | Sidewall ban | Standard format | ☐ Tersedia | ☐ Complete
4 | Pattern / Tipe | Pattern/model ban | S3C8 PLUS, R151, XDA2+, LM214 | ✓ Wajib | Sidewall ban | From pattern list | ☐ Tersedia | ☐ Complete
5 | DOT Code / Production Date | Kode DOT (tanggal produksi) | 3524 (week 35, year 2024) | ○ Optional | Sidewall ban | 4 digit WWYY | ☐ Tersedia | ☐ Complete
6 | Purchase Date | Tanggal pembelian | 2025-01-15 | ✓ Wajib | Invoice/PO | Date YYYY-MM-DD | ☐ Tersedia | ☐ Complete
7 | Purchase Price (Rp) | Harga beli per ban | 4500000, 5200000 | ✓ Wajib | Invoice | Numeric, >0 | ☐ Tersedia | ☐ Complete
8 | Supplier / Vendor | Nama supplier | PT Ban Jaya, UD Tire Center | ✓ Wajib | PO/Invoice | Text | ☐ Tersedia | ☐ Complete
9 | PO Number | Nomor purchase order | PO-2025-001 | ○ Optional | PO document | Alphanumeric | ☐ Tersedia | ☐ Complete
10 | Current Status | Status ban saat ini | Stock, Active (installed), Repair, Scrap | ✓ Wajib | Visual check | From status list | ☐ Tersedia | ☐ Complete
11 | Warehouse Location | Lokasi penyimpanan (jika stock) | Gudang A - Rak B2, Workshop Jakarta | Conditional | Warehouse log | From location master | ☐ Tersedia | ☐ Complete | If Status=Stock
12 | Condition at Purchase | Kondisi saat beli | NEW, RETREAD, SECOND | ✓ Wajib | Inspection | From condition list | ☐ Tersedia | ☐ Complete
13 | OTD - Original Tread Depth (mm) | Kedalaman tapak awal | 18.5, 19.0, 16.5 | ✓ Wajib | Measurement | Numeric, 10-25 | ☐ Tersedia | ☐ Complete
14 | Current RTD (mm) | Tread depth saat ini | 18.5, 14.2, 8.5 | Conditional | Measurement | Numeric, 0-OTD | ☐ Tersedia | ☐ Complete | If installed
15 | Standard PSI | Tekanan angin standar untuk ban ini | 130, 150, 160 | ✓ Wajib | Spec sheet | Numeric, 80-200 | ☐ Tersedia | ☐ Complete
16 | Load Index | Indeks beban ban | 146, 154, 156 | ○ Optional | Sidewall ban | Numeric, 100-200 | ☐ Tersedia | ☐ Complete
17 | Speed Rating | Rating kecepatan | K, L, M | ○ Optional | Sidewall ban | Single letter | ☐ Tersedia | ☐ Complete
18 | Ply Rating (PR) | Jumlah lapis ban | 14PR, 16PR, 18PR | ○ Optional | Sidewall ban | Number + 'PR' | ☐ Tersedia | ☐ Complete
19 | Warranty Period (months) | Masa garansi dari supplier | 12, 18, 24 | ○ Optional | Supplier doc | Numeric, 0-60 | ☐ Tersedia | ☐ Complete
20 | Expected Lifetime (km) | Target lifetime berdasarkan brand/size | 45000, 60000, 80000 | ○ Optional | Historical / Supplier | Numeric, >0 | ☐ Tersedia | ☐ Complete
--- DATA TAMBAHAN JIKA BAN SUDAH TERPASANG (INSTALLED) ---
21 | Vehicle / No. Polisi | Kendaraan tempat ban terpasang | DD 999 RI | Conditional | Field check | From vehicle master | ☐ Tersedia | ☐ Complete | If Status=Active
22 | Tire Position | Posisi ban di kendaraan | LF/1, RF/2, LMI/3, RRO/10 | Conditional | Field check | From position master | ☐ Tersedia | ☐ Complete | If Status=Active
23 | Installation Date | Tanggal pemasangan | 2025-01-20 | Conditional | Field log | Date YYYY-MM-DD | ☐ Tersedia | ☐ Complete | If Status=Active
24 | Installation KM/HM | KM/HM saat pemasangan | 125000 km, 5500 HM | Conditional | Vehicle odometer | Numeric, >0 | ☐ Tersedia | ☐ Complete | If Status=Active
25 | Mount Count | Berapa kali ban ini sudah dipasang | 1, 2, 3 | Conditional | History log | Integer, 1-5 | ☐ Tersedia | ☐ Complete | Track reuse

## 4. Master Data Lainnya
MASTER DATA PENDUKUNG (LOCATION, BRAND, SUPPLIER, FAILURE CODES)
No | Master Data Type | Data Required | Format / Contoh | Jumlah Minimal | Template | Status | Catatan
A. MASTER LOKASI (LOCATIONS)
1 | Warehouse / Site Name | Nama lokasi penyimpanan atau operasi | Gudang Jakarta A, Site Kalimantan, Workshop Surabaya | 3-10 locations | ☐ Tersedia | ☐ Complete
2 | Location Code | Kode singkat lokasi (optional) | JKT-A, KAL-01, SBY-W | Same as above | ☐ Tersedia | ☐ Complete
3 | Address | Alamat lengkap | Jl. Raya Industri No. 123, Jakarta | Same as above | ☐ Tersedia | ☐ Complete
4 | PIC / Coordinator | Penanggung jawab lokasi | Budi Santoso (HP: 08123456789) | Same as above | ☐ Tersedia | ☐ Complete
5 | Location Type | Jenis lokasi | Warehouse, Workshop, Operational Site, Head Office | Same as above | ☐ Tersedia | ☐ Complete
B. MASTER BRAND BAN (TIRE BRANDS)
6 | Brand Name | Nama brand ban yang digunakan | MRF, Bridgestone, Michelin, GT Radial | 2-10 brands | ☐ Tersedia | ☐ Complete
7 | Tier Level | Kategori brand | Premium, Standard, Economy | Same as above | ☐ Tersedia | ☐ Complete
8 | Country of Origin | Negara asal (optional) | India, Japan, France, Indonesia | Same as above | ☐ Tersedia | ☐ Complete
9 | Warranty Terms | Standar garansi dari brand | 12 months / 45,000 km | Same as above | ☐ Tersedia | ☐ Complete
10 | Average Lifetime (km) | Expected performance untuk brand ini | 45000, 60000, 80000 | Same as above | ☐ Tersedia | ☐ Complete
C. MASTER SUPPLIER / VENDOR
11 | Supplier Name | Nama perusahaan supplier ban | PT Ban Jaya Abadi, UD Tire Center | 2-5 suppliers | ☐ Tersedia | ☐ Complete
12 | Contact Person | PIC dari supplier | John Doe (08123456789, john@banjaya.com) | Same as above | ☐ Tersedia | ☐ Complete
13 | Address | Alamat supplier | Jl. Industri No. 456, Bekasi | Same as above | ☐ Tersedia | ☐ Complete
14 | Payment Terms | Syarat pembayaran | NET 30, Cash on Delivery, 50% DP | Same as above | ☐ Tersedia | ☐ Complete
15 | Brands Supplied | Brand apa saja yang disupply | MRF, GT Radial | Same as above | ☐ Tersedia | ☐ Complete
D. MASTER FAILURE CODES (KODE KERUSAKAN)
16 | Failure Code | Kode singkat kerusakan | AUS (Abnormal Uneven Shoulder), BNT (Burst) | 10-20 codes | ☐ Tersedia | ☐ Complete | Standard codes provided
17 | Description | Deskripsi kerusakan | Tapak aus tidak merata di bahu ban | Same as above | ☐ Tersedia | ☐ Complete
18 | Category | Kategori kerusakan | Wear, Damage, Manufacturing Defect | Same as above | ☐ Tersedia | ☐ Complete
19 | Root Cause | Penyebab umum | Under inflation, Overload, Misalignment | Same as above | ☐ Tersedia | ☐ Complete
20 | Prevention | Cara pencegahan | Check PSI daily, Reduce load | Same as above | ☐ Tersedia | ☐ Complete
21 | Claimable? | Apakah bisa di-claim ke supplier | Yes / No / Conditional | Same as above | ☐ Tersedia | ☐ Complete
E. MASTER TIRE SIZE
22 | Size Code | Ukuran ban standar yang digunakan | 10.00R20, 11.00R20, 295/80R22.5 | 3-10 sizes | ☐ Tersedia | ☐ Complete
23 | Diameter (mm) | Diameter ban (optional) | 1015, 1080 | Same as above | ☐ Tersedia | ☐ Complete
24 | Width (mm) | Lebar ban (optional) | 255, 295 | Same as above | ☐ Tersedia | ☐ Complete
25 | Standard OTD (mm) | Original tread depth standar | 18.5, 19.0 | Same as above | ☐ Tersedia | ☐ Complete
26 | Standard PSI Range | Rentang tekanan yang direkomendasikan | 130-160, 140-170 | Same as above | ☐ Tersedia | ☐ Complete
27 | Application | Rekomendasi penggunaan | Steer, Drive, Trailer | Same as above | ☐ Tersedia | ☐ Complete

## 5. SOP & Training
CHECKLIST SOP, TRAINING & KNOWLEDGE TRANSFER
No | Item / Kegiatan | Deskripsi | Deliverable / Output | PIC | Timeline | Status | Catatan
A. SOP & DOKUMENTASI
1 | SOP Tire Installation | Prosedur pemasangan ban yang benar | Dokumen SOP (PDF/Word) + Training video | CPH + Customer | Week 1 | ☐ Selesai
2 | SOP Tire Removal & Scrap | Prosedur pelepasan dan kriteria scrap ban | Dokumen SOP + Failure code guide | CPH + Customer | Week 1 | ☐ Selesai
3 | SOP Daily Inspection | Panduan inspeksi harian (driver & mekanik) | Checklist form + Mobile app guide | CPH + Customer | Week 1 | ☐ Selesai
4 | SOP Tire Rotation | Jadwal dan prosedur rotasi ban | Rotation schedule template | CPH + Customer | Week 1 | ☐ Selesai
5 | SOP Data Entry | Cara input data yang benar ke sistem | User manual + Screenshot guide | CPH | Week 1 | ☐ Selesai
6 | SOP Report Generation | Cara generate & interpret report | Report guide + Sample reports | CPH | Week 2 | ☐ Selesai
7 | Barcode Scanner Usage | Cara menggunakan barcode scanner | Quick reference card | CPH | Week 1 | ☐ Selesai
B. TRAINING & ORIENTATION
8 | Training for Fleet Manager | Overview sistem, dashboard, reporting | 2-3 jam sesi online/offline | CPH Trainer | Week 2 | ☐ Selesai | 1-2 peserta
9 | Training for Supervisor | Monitoring, approval, alert management | 2 jam sesi praktik | CPH Trainer | Week 2 | ☐ Selesai | 2-5 peserta
10 | Training for Admin/Operator | Input data installation/removal/inspection | 3 jam sesi hands-on | CPH Trainer | Week 2-3 | ☐ Selesai | 5-10 peserta
11 | Training for Driver | Daily inspection via mobile app | 1 jam sesi simple | CPH Trainer | Week 3 | ☐ Selesai | 10-50 peserta
12 | Training for Management | Read-only dashboard & report interpretation | 1 jam presentation | CPH Trainer | Week 2 | ☐ Selesai | 1-5 peserta
13 | Refresher Training (optional) | Review setelah 1 bulan penggunaan | 1-2 jam Q&A session | CPH Trainer | Month 2 | ☐ Selesai | Optional
C. KNOWLEDGE TRANSFER
14 | System Architecture Briefing | Penjelasan teknis sistem (untuk IT team) | Architecture diagram + Tech doc | CPH Tech | Week 1 | ☐ Selesai | If requested
15 | Database Schema Explanation | Struktur database (untuk IT team) | ER diagram + Data dictionary | CPH Tech | Week 1 | ☐ Selesai | If requested
16 | API Documentation | Dokumentasi API untuk integrasi | API spec (Swagger/Postman) | CPH Tech | Week 1-2 | ☐ Selesai | If integration needed
17 | Troubleshooting Guide | Panduan mengatasi masalah umum | FAQ document + Contact support | CPH Support | Week 2 | ☐ Selesai
D. MATERIAL & ASSET
18 | User Manual (Bahasa) | Manual penggunaan lengkap | PDF manual (ID & EN) | CPH | Week 2 | ☐ Selesai
19 | Video Tutorial | Video panduan penggunaan sistem | 5-10 video (2-5 menit each) | CPH | Week 2-3 | ☐ Selesai
20 | Quick Reference Card | Cheat sheet untuk operator | 1-page printable guide | CPH | Week 2 | ☐ Selesai
21 | Barcode Scanner (Hardware) | Scanner untuk input serial number | USB/Bluetooth scanner | Customer procure | Week 1 | ☐ Selesai | Customer provides
22 | Tablet/Smartphone | Untuk input data di lapangan | Android/iOS device | Customer procure | Week 1 | ☐ Selesai | Customer provides

## 6. Timeline Milestones
PROJECT TIMELINE & MILESTONES (TYPICAL 3-4 WEEK ONBOARDING)
Week | Phase | Activities | Deliverables | Customer | CPH | Status | Notes
W0 | Contract | Contract signing, kickoff | Signed contract, project charter | Sign & assign PIC | Setup project | ☐
W1 | Data Collection | Collect all master data | Vehicle/Tire data Excel 100% | Fill templates | Review & import | ☐ | CRITICAL
W1 | Data - Tires Stock | Inventory & barcode tagging | Stock tire data + barcodes | Physical count & tag | Import data | ☐ | CRITICAL
W1 | Data - Tires Installed | Map tires to vehicles | Tire-vehicle mapping | Measure RTD/PSI | Import mapping | ☐ | CRITICAL
W1 | SOP Review | Customize & approve SOP | Agreed SOP documents | Review & approve | Draft & finalize | ☐
W2 | System Setup | Create users & configure | Active accounts | Test login | Create accounts | ☐
W2 | Training - Mgmt | Fleet Manager training | Training materials | Attend 2-3 jam | Conduct training | ☐
W2 | Training - Supervisor | Supervisor training | Training materials | Attend 2 jam | Conduct training | ☐
W2 | UAT Testing | Test all modules | UAT sign-off | Test thoroughly | Fix bugs | ☐
W3 | Training - Operators | Admin/operator training | Hands-on practice | Practice entry | Conduct 3 jam | ☐
W3 | Training - Drivers | Driver mobile app training | Quick reference | Attend 1 jam | Conduct training | ☐
W3 | Soft Launch | Start limited usage | First week transactions | Input real data | Monitor 24/7 | ☐ | CRITICAL
W3 | Data Verification | Verify all data loaded | Verification report | Review & confirm | Run validation | ☐
W4 | Go-Live Prep | Final check & backup | Go-Live checklist | Confirm ready | Final check | ☐
W4 | Official Go-Live | Full activation | Active system | Use for all txn | Monitor 24/7 | ☐ | 🎉
W4 | Handover | Transfer to support | Handover doc | Sign handover | Transfer support | ☐
M2 | Hypercare | 30-day intensive support | Daily reports | Report issues | Quick resolution | Ongoing
M2+ | Regular Support | Standard SLA support | Monthly/Quarterly review | Use system | Ongoing support | Ongoing

## 7. Pre-GoLive Checklist
PRE-GO-LIVE FINAL CHECKLIST (MUST BE 100% COMPLETE)
No | Item | Criteria | How to Verify | Status | Notes
1 | Vehicle data 100% complete | All vehicles entered | Dashboard count = actual | ☐
2 | Stock tire data 100% | All stock tires registered | Physical = system | ☐
3 | Installed tires mapped | All tires on vehicles mapped | No empty positions | ☐
4 | Current KM accurate | All odometer readings current | Verify vs actual | ☐
5 | RTD measured | All tires have RTD | Spot check 10% | ☐
6 | User accounts created | All users can login | Test each account | ☐
7 | Fleet Manager trained | Understands reporting | Can generate reports | ☐
8 | Supervisors trained | Understand workflows | Can approve movements | ☐
9 | Operators trained | Can enter data fast | Complete form <2 min | ☐
10 | SOP distributed | All have SOP | Signed acknowledgment | ☐
11 | Installation works | Can install tire | Test real serial | ☐
12 | Removal works | Can remove tire | Test workflow | ☐
13 | Inspection works | Can record inspection | Test multiple tires | ☐
14 | Dashboard loads | Shows correct data | All KPIs correct | ☐
15 | Reports work | Can export | Test Excel/PDF | ☐
16 | Barcode scanner works | Scans serial numbers | Test 10 tires | ☐
17 | Mobile works | Access on phones | Test Android/iOS | ☐
18 | Alerts working | Sends notifications | Test critical alert | ☐
19 | Internet stable | Workshop connectivity | Speed >5 Mbps | ☐
20 | Support contact known | Team knows hotline | Contact displayed | ☐
21 | Barcode stickers ready | Sufficient stock | 500+ available | ☐
22 | Measurement tools ready | Gauge calibrated | Tools working | ☐
23 | Customer PIC sign-off | Ready to go-live | Signed approval | ☐
24 | CPH PM sign-off | System ready | Signed certificate | ☐
25 | Go-Live date confirmed | Date set & communicated | Team aware | ☐